## example
ID | Task | Start Date | End Date | Duration
1 | TaskA | 2020-04-15 | 2020-04-17 | 2
1.1 | TaskD | 2020-04-18 | 2020-04-20 | 2 | 2020-04-15 | 2020-04-28
2 | TaskB | 2020-04-21 | 2020-04-22 | 1 | 43936 | 43949
3 | TaskC | 2020-04-23 | 2020-04-24 | 1
4 | TaskE | 2020-04-25 | 2020-04-26 | 1
5 | TaskF | 2020-04-27 | 2020-04-28 | 1

## Exercise1
|  | Start Date | End Date | Duration
1 | Diagram of the process flow of Purchases, Sales and Inventories. | 2020-04-15 | 2020-04-17 | 2
2 | Fields definition for every process. | 2020-04-18 | 2020-04-19 | 1
3 | Create field columns of every process in Excel worksheet. | 2020-04-20 | 2020-04-21 | 1
4 | Team test to enter the values of every process field and excel worksheet. | 2020-04-22 | 2020-04-24 | 2
5 | Creation of filters and Pivot Tables for every Process's Excel Worksheet. | 2020-04-25 | 2020-04-27 | 2
7 | Definition of reports and information to get from filters and Pivot Tables for every process. | 2020-04-28 | 2020-04-30 | 2
8 | Training for each area to implement the Excel Worksheets. | 2020-05-01 | 2020-05-04 | 3
[5 empty] | 43936 | 43955

## APM
|  | Start Date | End Date | Duration
1 | Inventory of Servers | 2020-04-15 | 2020-04-17 | 2
2 | Define metrics to measure | 2020-04-18 | 2020-04-20 | 2
3 | Database query performance. | 2020-04-18 | 2020-04-20 | 2
4 | Identification of web apps | 2020-04-22 | 2020-04-24 | 2
5 | Code injection on Web pages | 2020-04-25 | 2020-04-27 | 2
7 | Installation of metrics server | 2020-04-28 | 2020-04-29 | 1
8 | Test dashboards of performance in Physical | 2020-04-30 | 2020-05-01 | 1
[5 empty] | 2020-04-15 | 2020-05-01
[5 empty] | 43936 | 43952

## Sheet1
|  | Start Date | End Date | Duration
1 | Inventory of Servers | 2020-04-15 | 2020-04-17 | 2
2 | Define metrics to measure | 2020-04-18 | 2020-04-20 | 2
3 | Database query performance. | 2020-04-18 | 2020-04-20 | 2
4 | Identification of web apps | 2020-04-22 | 2020-04-24 | 2 | 2020-04-15 | 2020-05-01
5 | Code injection on Web pages | 2020-04-25 | 2020-04-27 | 2 | 43936 | 43952
7 | Installation of metrics server | 2020-04-28 | 2020-04-29 | 1
8 | Test dashboards of performance in Physical | 2020-04-30 | 2020-05-01 | 1

## InventorySales
|  | Start Date | End Date | Duration
1 | Diagram of the process flow | 2020-04-15 | 2020-04-17 | 2
2 | Fields definition for every process | 2020-04-18 | 2020-04-19 | 1
3 | Create field columns of every process | 2020-04-20 | 2020-04-21 | 1
4 | Enter values in Excel sheet | 2020-04-22 | 2020-04-24 | 2
5 | Create filters and Pivot Tables | 2020-04-25 | 2020-04-27 | 2
7 | Definition of Reports | 2020-04-28 | 2020-04-30 | 2
8 | Training to users | 2020-04-30 | 2020-05-02 | 2
[5 empty] | 2020-04-15 | 2020-05-02
[5 empty] | 43936 | 43953